## Лист1
# | Task | Original estimate | Remaining estimate | Assigne | Reporter
1 | Analyze the needs of your audience | 1 |  | Alikhan
2 | Examine the context and purpose of the study | 1 |  | Alikhan
3 | Organize the information into content sections | 1 |  | Alikhan
4 | Planning the division of the team | 1
5 | Definition of project objectives | 2 |  | Giorgio
6 | Project sponsorship research | 1 |  | Giorgio
7 | Make a budget estimate of the project costs | 1 |  | Giorgio
8 | Choosing the Server | 1 |  | Giorgio
9 | Choosing the Database | 1 |  | Giorgio
10 | Creating the Database | 3 |  | Giorgio
11 | Global data collection about football | 3 |  | Giorgio
12 | Choose the development to environment | 2 |  | Giorgio
13 | Creting main page UI | 1 |  | Aidos
14 | Creating registration UI and Log in | 1 |  | Aidos
15 | Creating the All score page of UI | 1 |  | Aidos
16 | Creating the Deatil news and match of UI | 1 |  | Aidos
17 | Create a logo | 1 |  | Aidos
18 | Creating registration and Log in code | 2 |  | Simone
19 | Creating the All score page code | 4 |  | Kydyrali
20 | Creating the All news page code | 4 |  | Kydyrali
21 | Creating the Deatil news and match code | 3 |  | Kydyrali
22 | Code testing | 7 |  | Kydyrali
23 | Creating a documentation | 3 |  | Nishi
24 | Distribution | 1 |  | Nishi