## Лист1
# | Task | Original estimate | Remaining estimate | Assigne | Reporter
1 | Preparing feasibility report | 4 |  | Alikhan
2 | Analyze the needs of your audience | 1 |  | Alikhan
3 | Examine the context and purpose of the study | 1
4 | Organize the information into content sections | 1
5 | Determine the order of the information | 1
6 | Planning the division of the team | 1
7 | Definition of project objectives | 2 |  | Giorgio
8 | Project sponsorship research | 1
9 | Make a budget estimate of the project costs | 1 |  | Giorgio
10 | Choosing the Server | 1
11 | Choosing the Database | 1
12 | Creating the Database | 3
13 | Global data collection about football | 3
14 | Choose the development to environment | 2
15 | Create the design for application | 6 |  | Aidos
16 | Creting main page UI | 1 |  | Aidos
17 | Creating registration UI and Log in | 1
18 | Creating the All score page of UI | 1 |  | Aidos
19 | Creating the All news page of UI | 1
20 | Creating the Deatil news and match of UI | 1 |  | Aidos
21 | Create a logo | 1
22 | Code development | 23 |  | Simone
23 | Creting main page code | 3
24 | Creating registration and Log in code | 2 |  | Simone
25 | Creating the All score page code | 4 |  | Kydyrali
26 | Creating the All news page code | 4
27 | Creating the Deatil news and match code | 3 |  | Kydyrali
28 | Code testing | 7
29 | Creating a documentation | 3 |  | Nishi
30 | Distribution | 1 |  | Nishi