## TASKS
# | Task | Original estimate | Remaining estimate | Assigne | Reporter
1 | Preparing feasibility report | 4
2 | Analyze the needs of your audience | 1 |  | Alikhan
3 | Examine the context and purpose of the study | 1 |  | Alikhan
4 | Organize the information into content sections | 1 |  | Alikhan
5 | Determine the order of the information | 1 |  | Alikhan
6 | Planning the division of the team | 1 |  | Giorgio
7 | Definition of project objectives | 2 |  | Giorgio
8 | Project sponsorship research | 1 |  | Giorgio
9 | Make a budget estimate of the project costs | 1 |  | Giorgio |  | TOTAL | 52 | DAYS
10 | Choosing the Server | 1 |  | Metin
11 | Choosing the Database | 1 |  | Metin
12 | Creating the Database | 3 |  | Metin
13 | Global data collection about football | 3 |  | Metin
14 | Choose the development to environment | 2
15 | Create the design for application | 6
16 | Creting main page UI | 1 |  | Aidos
17 | Creating registration UI and Log in | 1 |  | Aidos
18 | Creating the All score page of UI | 1 |  | Aidos
19 | Creating the All news page of UI | 1 |  | Aidos
20 | Creating the Deatil news and match of UI | 1 |  | Aidos
21 | Create a logo | 1 |  | Kydyrali
22 | Code development | 23
23 | Creting main page code | 3 |  | Simone
24 | Creating registration and Log in code | 2 |  | Simone
25 | Creating the All score page code | 4 |  | Kydyrali
26 | Creating the All news page code | 4 |  | Kydyrali
27 | Creating the Deatil news and match code | 3 |  | Simone
28 | Code testing | 7 |  | Himanshi
29 | Creating a documentation | 3 |  | Himanshi
30 | Distribution | 1 |  | Himanshi

## BRD
1
1.1

## CAPACITY
RESOURCING PLAN |  |  | DAYS | No workink DAYS
Start date for development |  | 2017-11-01
End date (Code complete) |  | 2018-01-22 | 52 | 30
Begin regression testing |  | 2018-01-25 | 3
Gold version |  | 2018-02-13 | 13 | 6
Production release date |  | 2018-02-19 | 4 | 2
Dev days in period |  |  | 72
Non-feature development (Poland) |  |  | 0%
Poland holidays in period |  |  | 38
R&D projects Poland |  |  | 10%
Whole cycle: | DAYS | 110 | WEEKS | 15.7143

## CAPACITY 2
Developer | Location | Holidays-office closed | Planned time off | SUPPORT and UNEXPECTED | R&D days | Productivity factor | Extra hours | Raw productivity days
Metin | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
Giorgio | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
Simone | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
Aidos | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
Alikhan | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
Himanshi | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
Kydyrali | Poland | 38 | 2 | 3 | 1 | 100% | - | 52
TOTAL |  | 266 | 14 | 21 | 7 | 100% | 0 | 364
PROJECTS IN % |  |  |  |  | PROJECTS IN DAYS

## BEFORE RELASE
BEFORE RELASE |  |  | ENU
IDENTIFIER | NAME | OWNER | STG | PRD
B1 | backup | OPS | TBD | TBD
database
configuration
settings
code
B2 | changes on servers | OPS
proprieties
hardware
configuration
settings
B3 | privigies
DURING RELASE
D1 | release package
AFTER RELASE
A1 | test | QA
A2 | turn on | OPS
A3 | confirmation message | OPS/PM