## Main Page
# | Tasks | Asignee | Reporter | Issue | Summary | Component | priority | due date | Fix version | Environment | Attachments
1 | Preparing feasibility report | Aidos | Giorgio | task | DONE | reports | Low | 2017-10-02 | 1,1,0 | planning | text, table
2 | Analyze the needs of your audience | Metin | Metin | task | DONE | reports | Low | 2017-10-03 | 1,1,0 | planning | text, table
3 | Examine the context and purpose of the study | Aidos | Simone | task | DONE | involves | Low | 2017-10-05 | 1,1,0 | planning | text, table
4 | Organize the information into content sections | Kydyrali | Aidos | task | DONE | reports | Low | 2017-10-08 | 1,1,0 | Planning | text, table,grapichs
5 | Determine the order of the information | Giorgio | Metin | task | DONE | reports | normal | 2017-10-10 | 1,1,0 | planning | text, table
6 | Planning the division of the team | Aidos | Giorgio | task | TBD | reports | normal | 2017-10-12 | 1,1,0 | planning | text, table
7 | Definition of project objectives | Alikhan | Metin | task | DONE | involves | normal | 2017-10-17 | 1,1,0 | Planning | text, table
8 | Project sponsorship research | Simone | Kydyrali | task | TBD | reports | normal | 2017-10-20 | 1,1,0 | Planning | text, table
9 | Make a budget estimate of the project costs | Kydyrali | Giorgio | task | TBD | reports | normal | 2017-10-26 | 1,1,0 | Developing | text
10 | Choosing the Server | Alikhan | Metin | task | TBD | reports | normal | 2017-11-01 | 1,1,0 | Developing | text
11 | Choosing the Database | Simone | Kydyrali | task | DONE | reports | normal | 2017-11-05 | 1,1,0 | Developing | text, table
12 | Creating the Database | Metin | Giorgio | task | DONE | reports | High | 2017-11-09 | 1,1,0 | Developing | text
13 | Global data collection about football | Alikhan | Metin | task | DONE | reports | normal | 2017-11-12 | 1,1,0 | Developing | text, table
14 | Choose the development to environment | Simone | Kydyrali | task | DONE | involves | normal | 2017-11-15 | 1,1,0 | Developing | text
15 | Create the design for application | Aidos | Giorgio | task | In Progress | reports | normal | 2017-11-17 | 1,1,0 | Developing | program
16 | Creting main page UI | Alikhan | Metin | task | In Progress | reports | normal | 2017-11-20 | 1,1,0 | Developing | documents
17 | Creating registration UI and Log in | Simone | Kydyrali | task | In Progress | reports | normal | 2017-11-22 | 1,1,0 | Developing | documents
18 | Creating the All score page of UI | Aidos | Giorgio | task | In Progress | reports | normal | 2017-11-24 | 1,1,0 | Developing | documents
19 | Creating the All news page of UI | Alikhan | Metin | task | In Progress | reports | normal | 2017-11-26 | 1,1,0 | Developing | documents
20 | Creating the Deatil news and match of UI | Simone | Kydyrali | task | In Progress | reports | normal | 2017-11-30 | 1,1,0 | Developing | product
21 | Create a logo | Alikhan | Giorgio | task | DONE | reports | Low | 31.11.2017 | 1,1,0 | Developing | text, table,grapichs
22 | Code development | Alikhan | Metin | task | DONE | reports | Low | 2017-12-04 | 1,1,0 | Developing | program
23 | Creating main page code | Simone | Kydyrali | task | DONE | involves | Low | 2017-12-07 | 1,1,0 | Testing | program
24 | Creating registration and Log in code | Giorgio | Giorgio | task | DONE | reports | Low | 2017-12-10 | 1,1,0 | Testing | program
25 | Creating the All score page code | Alikhan | Metin | task | In Progress | reports | normal | 2017-12-14 | 1,1,0 | Testing | program
26 | Creating the All news page code | Simone | Kydyrali | task | In Progress | reports | normal | 2017-12-17 | 1,1,0 | Testing | program
27 | Creating the Deatil news and match code | Aidos | Giorgio | task | In Progress | involves | normal | 2017-12-20 | 1,1,0 | Testing | program
28 | Code testing | Alikhan | Metin | task | DONE | reports | normal | 2017-12-22 | 1,1,0 | Testing | program
29 | Creating a documentation | Simone | Kydyrali | task | DONE | reports | normal | 2018-01-03 | 1,1,0 | Developing | documents
30 | Distribution | Aidos | Giorgio | task | DONE | reports | normal | 2018-01-08 | 1,1,0 | Developing | documents
[8 empty] | 2018-01-09 | Production

## DeliveryDates
TASK Name | Date
Start Date for development | 2017-10-02
End date (code complete) | 2018-01-08
Begin Regression Date | 2017-11-20
Gold version | 2017-12-23
Production release date | 2018-01-09

## TeamCapacity1
Resourcing Plan |  | Days | Net Days
Start Date for development
End date (code complete) |  | 98 | 36
Begin Regression Date
Gold version
Production release date
Dev Days in period | 98
Supported/unexpected | 0
National holidays | 3
R&D projects | 0.05

## TeamCapacity2
Developer | Location | Holidays-office closed | Planed time off | Support and unexpected | R&D days | Productivity factor % | Extra hours | Raw productivity days | Equivalent development days | Столбец1
Giorgio | Italy | 4 | 2 | 0 | 1.8 | 10 | 0 | 28.2 | 2.82
Simone | Italy | 8 | 2 | 0 | 1.8 | 40 | 3 | 21.2 | 8.48
Metin | Turkey | 4 | 2 | 0 | 1.8 | 0 | 1 | 27.2 | 0
Aidos | Kazakhstan | 4 | 2 | 0 | 1.8 | 35 | 3 | 25.2 | 8.82
Kydyrali | Kazakhstan | 2 | 2 | 0 | 1.8 | 10 | 0 | 30.2 | 3.02
Alikhan | Kazakhstan | 4 | 2 | 0 | 1.8 | 45 | 2 | 26.2 | 11.79
|  | 26 | 12 | 0 | 10.8 | 23.3333 | 9 | 158.2 | 34.93

## Dashboard
Planning | Developing | Testing
40 | 80 | 30
TBD | DONE | In Progress
20 | 85 | 45

## ReleaseList
| Owner | Enviroment
|  | Stage | Product
Identity release version | QA | 1,1,1 | 1,1,1
Location of package | QA | Product | TBD
Release date | PM | 2018-01-10 | 2018-01-25
Release status | OPS | DONE | TBD
Realease dev | DEV lead | Alikhan | Kydyrali
| QA lead | Aidos | Giorgio
| OPS | Metin | Simone
Release contact | DEV | amantayev.alikhan055@gmail.com,
Approval | QA | DONE | TBD
| DEV | DONE | TBD
| OPS | DONE | TBD
Release maintenance | OPS | 5 hours | 8 hours
Before release
Backup :
DB | OPS | DONE | TBD
Configuration | OPS | DONE | TBD
Settings | OPS | DONE | TBD
Code | DEV | DONE | TBD
Changes on sever
Properties | OPS | DONE | TBD
Hardware | Tech team | DONE | TBD
Configurations | OPS | DONE | TBD
Settngs | OPS | DONE | TBD
During Release
Release Package | https://www.footballapp.com
After Release
Test | QA | DONE | TBD
Turn on | OPS | TBD | TBD
Confirmation message | OPS/PM

## HolidaysCalc
Country | Total holidays
Italy | 12
Kazakhstan | 10
Turkey | 4
Date | Alikhan | Kydyrali | Martin | Aidos | Giogrio | Simone
2017-10-01
2017-10-02 | 1 |  |  | 1
2017-10-03 |  | 1
2017-10-04 |  |  |  |  | 1
2017-10-05
2017-10-06
2017-10-07
2017-10-08 |  |  | 1 |  | 1
2017-10-09
2017-10-10
2017-10-11
2017-10-12 | 1
2017-10-13
2017-10-14
2017-10-15 | 1
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25 |  | 1 |  |  | 1
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30 | [5 empty] | 1
2017-10-31
2017-11-01 | 1
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07 |  |  | 1
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14 | [5 empty] | 1
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21 | 1
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28 |  | 1
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03 | 1
2017-12-04
2017-12-05 |  |  |  | 1
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11 | 1 |  |  |  |  | 1
2017-12-12
2017-12-13
2017-12-14 |  |  | 1
2017-12-15
2017-12-16
2017-12-17
2017-12-18 |  |  |  |  | 1
2017-12-19 |  | 1
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03 | 1
2018-01-04
2018-01-05 | [5 empty] | 1
2018-01-06
2018-01-07
2018-01-08 |  |  | 1
2018-01-09

## Sprints
Sprint1 | TBD | In Progress | DONE
#1Preparing feasibility report
#2Analyze the needs of your audience
#3Examine the context and purpose of the study
#4Organize the information into content sections
Sprint2 |  |  | #1Determine the order of the information
#2Planning the division of the team
#3Definition of project objectives
#4Project sponsorship research
Sprint3 | #1Make a budget estimate of the project costs
#2Choosing the Server
#3Choosing the Database
#4Creating the Database
Sprint4 |  |  | #1Global data collection about football
#2Choose the development to environment
#3Create the design for application
#4Creting main page UI
#5Creating registration UI and Log in
Sprint5 |  | #1Creating the All score page of UI
#2Creating the All news of UI
#3Creating the Deatil news and match of UI
#4Create a logo
Sprint6 |  |  | #1Code development
#2Creating main page code
#3Creating registration and Log in code
#4Creating the All score page code
#5Creating the All news page code
Sprint7 |  | #1Creating the Deatil news and match code
#2Code testing
#3Creating a documentation
#4Distribution

## BurndownC
| Hours |  | Remaining
Days | Actual | Planned | Actual | Planned
0 |  |  | 672 | 672
1 | 8 | 9 | 664 | 663
2 | 8 | 11 | 656 | 652
3 | 8 | 7 | 648 | 645
4 | 8 |  | 640 | 645
5 | 8 | 11 | 632 | 634
6 | 8 | 9 | 624 | 625
7 | 8 | 8 | 616 | 617
8 | 8 | 8 | 608 | 609
9 | 8 | 11 | 600 | 598
10 | 8 |  | 592 | 598
11 | 8 | 11 | 584 | 587
12 | 8 | 8 | 576 | 579
13 | 8 |  | 568 | 579
14 | 8 | 10 | 560 | 569
15 | 8 | 8 | 552 | 561
16 | 8 | 8 | 544 | 553
17 | 8 | 10 | 536 | 543
18 | 8 | 10 | 528 | 533
19 | 8 | 8 | 520 | 525
20 | 8 | 9 | 512 | 516
21 | 8 |  | 504 | 516
22 | 8 | 8 | 496 | 508
23 | 8 | 8 | 488 | 500
24 | 8 | 9 | 480 | 491
25 | 8 | 10 | 472 | 481
26 | 8 | 10 | 464 | 471
27 | 8 | 8 | 456 | 463
28 | 8 | 9 | 448 | 454
29 | 8 | 9 | 440 | 445
30 | 8 | 10 | 432 | 435
31 | 8 | 9 | 424 | 426
32 | 8 | 9 | 416 | 417
33 | 8 | 8 | 408 | 409 | Task | Total Hours
34 | 8 | 9 | 400 | 400 | Preparing feasibility report | 9
35 | 8 | 12 | 392 | 388 | Analyze the needs of your audience | 11
36 | 8 |  | 384 | 388 | Examine the context and purpose of the study | 18
37 | 8 | 7 | 376 | 381 | Organize the information into content sections | 17
38 | 8 | 9 | 368 | 372 | Determine the order of the information | 8
39 | 8 | 11 | 360 | 361 | Planning the division of the team | 11
40 | 8 | 10 | 352 | 351 | Definition of project objectives | 19
41 | 8 | 8 | 344 | 343 | Project sponsorship research | 18
42 | 8 |  | 336 | 343 | Make a budget estimate of the project costs | 28
43 | 8 | 11 | 328 | 332 | Choosing the Server | 17
44 | 8 | 9 | 320 | 323 | Choosing the Database | 16
45 | 8 | 8 | 312 | 315 | Creating the Database | 65
46 | 8 | 13 | 304 | 302 | Global data collection about football | 54
47 | 8 |  | 296 | 302 | Choose the development to environment | 38
48 | 8 | 12 | 288 | 290 | Create the design for application | 11
49 | 8 | 8 | 280 | 282 | Creting main page UI | 9
50 | 8 | 8 | 272 | 274 | Creating registration UI and Log in | 8
51 | 8 | 13 | 264 | 261 | Creating the All score page of UI | 8
52 | 8 | 11 | 256 | 250 | Creating the All news page of UI | 62
53 | 8 | 8 | 248 | 242 | Creating the Deatil news and match of UI | 26
54 | 8 | 10 | 240 | 232 | Create a logo | 6
55 | 8 |  | 232 | 232 | Code development | 32
56 | 8 | 13 | 224 | 219 | Creating main page code | 39
57 | 8 | 6 | 216 | 213 | Creating registration and Log in code | 37
58 | 8 | 7 | 208 | 206 | Creating the All score page code | 21
59 | 8 | 8 | 200 | 198 | Creating the All news page code | 14
60 | 8 | 9 | 192 | 189 | Creating the Deatil news and match code | 18
61 | 8 | 8 | 184 | 181 | Code testing | 26
62 | 8 |  | 176 | 181 | Creating a documentation | 18
63 | 8 | 10 | 168 | 171 | Distribution | 8
64 | 8 | 12 | 160 | 159 |  | 672
65 | 8 | 7 | 152 | 152
66 | 8 | 10 | 144 | 142
67 | 8 | 9 | 136 | 133
68 | 8 | 8 | 128 | 125
69 | 8 |  | 120 | 125
70 | 8 | 8 | 112 | 117
71 | 8 | 12 | 104 | 105
72 | 8 | 11 | 96 | 94
73 | 8 | 10 | 88 | 84
74 | 8 | 7 | 80 | 77
75 | 8 | 7 | 72 | 70
76 | 8 |  | 64 | 70
77 | 8 | 8 | 56 | 62
78 | 8 | 10 | 48 | 52
79 | 8 | 9 | 40 | 43
80 | 8 | 10 | 32 | 33
81 | 8 | 7 | 24 | 26
82 | 8 | 10 | 16 | 16
83 | 8 | 8 | 8 | 8
84 | 8 | 8 | 0 | 0

## RootForDates
Aidos | Bug | reports | Planning
Giorgio | Improvement | involves | Developing
Alikhan | Testing |  | testing
Metin | UI/UX |  | Production
Simone | task
Kydyrali | epic
data issue