## Foglio1
Name | What we have accomplished since the last meeting? | What we will do today? | What kind of troubles do we have?
Giorgio Macauda | I collected all information that we need to create our DB and I designed it. | I'm going to start a real implementation of it using MYSQL | I need a kind of script that can collect data automatically in order to test the correct functioning
Alikhan Amantayev | Yesterday I developed a logo on web pages. and also chose the colorful home page. | Today, I will putting the pictures into application. | The problems were with the quality of the picture, and also putting it in the application
Kydyrali Akhmet | During our last meeting, I made an approximate calculation of the budget estimates of the project costs. | Today we will distribute our funds. On what materials will be spent a certain amount of money. | We had small financial deficiencies, which I immediately decided.
Simone Rava | I have contributed to the choice of development environments, and I wrote part of the homepage code and other pages. | Today i start to write code of the news pages. | We are in a small delay with the code because of a problem with libraries implementation.
Metin Karagöz | I have fulfilled the test task required for the project to work on different operating systems and web sites | I'm going to check the app's mobile and browser suitability and At the same time, I will make the application run on older devices | The application is not working properly on android phones and there is some problems about live results and team informations